## Progress As of 31March2022 (2)
PLEASE UPDATE THE FISHERY REFUGIA PROGRESS AT COUNTRY LEVEL AS OF 30 JUNE 2022
Objective/ Targets | Outcomes | Results | Code | Expected Outputs | Cambodia | Indonesia | Malaysia | Philippines | Thailand | Viet Nam | Regional Programs | LINKs to Results
[5 empty] | (3+1 Sites) | (2 Sites) | (2 Sites) | (3 Sites) | (2 Sites) | (2-3 Sites)
1) Effective management of key threats to 14 fisheries refugia sites [269,500 ha], including ~50 percent reduction in fishing pressure within sites at times critical to the life-cycles of fished species of transboundary significance | Reduced stress on fish stocks and coastal habitats via improved national management of key anthropogenic threats to fisheries and critical habitat linkages | It is expected that by end of 2022, the effective management of 14 fisheries refugia about 660,236 ha, including effective management measures on reducing >50% fishing presusure that impact to refugia identified by stakeholders. | A01 | Fisheries refugia profile reports, including GIS maps & site characterisations, published
|  |  | A02 | Published management plans (Link to B02)
|  |  | A03 | Quarterly/Annual Technical reports of network meetings and activities (Number of reports) | 97 + ? | 36 + ? | 33 + ? | 57 + ? | 43 + ? | NA +? | 14 + 1 | Linked to Regional Refugia Website
2) National and regional policy, legal and planning frameworks for demarcating boundaries and managing fisheries refugia, resulting in, inter alia, a 20 percent increase in small-scale fishing vessels using fishing gear and practices designed to safeguard fish stock and critical habitat linkages at priority sites | Increased institutional capacity in the 6 participating countries for the designation and operational management of fisheries refugia via the transformation of enabling environments and the generation of knowledge for planning | National policy, legal and plannning framwork are being achieved, three of six countries completed, while the other three are in process for adoption by government. The effective management of fisheries refugia are not focused only increasing of small-scale fishing vessels that must use to the best practices fishing gears, but covering the medium and large scale fishing vessels that are >50% prohibited to operate in the refugia areas. The demercating boundaries refugia site are identified with the critical habitat linkages to ensure that the refugia designed to safeguard fish stock and critical habitat linkages. The Regional Action Plan for mannagement of fisheries refugia was adopted by six participatinng countries and scale-up covering the Southeast Asian Regiona under the ASEAN policy framework. | B01 | Published national reviews and recommendations for reforms of national regulations/ordinances
|  |  | B02 | Endorsed revised policies, Strategic Managment Plan, Fisheries Master Plan
|  |  | B03 | Published national guidelines on establishing and operating fisheries refugia
|  |  | B04 | National reports on policy, legal and institutional aspects of refugia establishment and management published
|  |  | B05 | Endorsed policy and executive orders, provincial/local ordinances and by-laws (proclamation, Provincial Orders for each site)
|  |  | B06 | Endorsed National Action Plan for the management of priority fisheries refugia and associated biodiversity
|  |  | B07 | Databases online and populated with datasets included fish stock | [6 empty] | Completed, uploaded to website | Linked to Regional Refugia Website
|  |  | B08 | Endorsed Regional Action Plan for fisheries refugia | cooperated | cooperated | cooperated | cooperated | cooperated | cooperated | Endorsed by SEAFDEC / ASEAN
|  |  | B09 | National and Regional Geographical Information System online | Link to A1 | [5 empty] | 1st online in 2021, updating in 2022
|  |  | B10 | Characterisations for 14 refugia sites accessible online | Link to A1
|  |  | B11 | Modelling system online | PSC2 agreed to apply the existing Modeling system developed by the IOC/WESTPAC due to lack of lomg term dataset.
|  |  | B12 | Best practice fishing methods and practices to address key threats to fish stock and critical habitat linkages | Link to B06, B05 (Mannagement Measures) | [5 empty] | Finalizing from Country inputs
3) National and regional systems for knowledge management and sharing, including the development of indicator sets and standardized statistics to guide the replication, scaling-up and mainstreaming of good practices in the use of fisheries refugia as a spatial planning tool | Strengthened knowledge management and information sharing and access for enhanced uptake of good practice in integrating fisheries management and biodiversity conservation in the design and implementation of fisheries and environmental management systems, including Marine Spatial Planning | Six countries are in process for enhancing the national systems for knowleadge management and sharing. Five Refugia Information Centres have been established in Malaysia and Philippines. Three national webportal are onlined, while other countries underways. The Regional website and Repository system are developed linking to the SEAFDEC network system. Regional Guidelines on Indicators is drafted for adoption by Project Steering Committee. | C01 | Best practice approaches and measures for integrated fisheries and habitat management | Included in Quarterly Reports | Included in Quarterly Reports | Included in Quarterly Reports | Included in Quarterly Reports | Included in Quarterly Reports | NA | Will be summarized and updated online by Q3/2022
|  |  | C02 | Public awareness and Outreach programmes including tracking of extent of community acceptance | via capacity building, consultations, Workshops |  |  |  |  | NA
|  |  | C03 | Education and awareness centre on fisheries and criticle habitat established | NA | NA | 3 refugia info centres established | 2 refugia info centres established | planning | NA
|  |  | C04 | Regional agreement/guidelines on indicators for managed refugia (including standardized data collection) | cooperated | cooperated | cooperated | cooperated | cooperated | cooperated | Adopted at PSC7 Adhoc
|  |  | C05 | Online national web portals on fisheries refugia | Developing | Created/onlined | Developing via lead agency website | Created/onlined | Created/onlined | NA | Completed, uploaded to website | Linked to Regional Refugia Website
4) Effective multi-lateral and intergovernmental communication and joint decision-making, including the use of a consensual knowledge-base in planning ecologically and cost-effective management actions | Cost-effective and efficient coordination of national and regional level cooperation for integrated fisheries and environmental management | National and regional cooperation and coordination for integrated fish stock and critical habitat management in the South China Sea and Gulf of Thailand | D01 | NFRC Terms of Reference and reports | TORs Completed (need updated) | TORs Completed (need updated) | TORs Completed (need updated) | TORs Completed (need updated) | TORs Completed (need updated) | NA
|  |  | D02 | NSTC Terms of Reference and reports | TORs Completed (need updated) | TORs Completed (need updated) | TORs Completed (need updated) | TORs Completed (need updated) | TORs Completed (need updated) | NA
|  |  | D03 | Management Board Terms of Reference and Reports | TORs Completed (need updated) | TORs Completed (need updated) | TORs Completed (need updated) | TORs Completed (need updated) | TORs Completed (need updated) | NA
|  |  | D04 | RSTC Terms of Reference and Reports | [6 empty] | TORs Completed (5 Reports)
|  |  | D05 | PSC Terms of Reference and Reports | [6 empty] | TORs Completed (7 Reports)
|  |  | D06 | Terms of Reference and contracts for project coordination unit staff | [6 empty] | TOR Completed